## Sheet1
RIST MACHINE REGISTER PLAN
[8 empty] | September #9 |  |  |  | October #10
Task ID | Task |  |  | Start Date | End Date | Duration (Days) | Status | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-10-01 | 2020-10-08 |  |  |  |  | 2020-10-15 |  | 2020-10-22
1 | Design interface and report
1.1 |  | Page 2 (Equipment Safety Device & Safety Cover Check Sheet)
1.2 |  |  | Design in asp.net HTML Bootstrap | 18/10/2019 | 19/10/2019 | 3 | Completed
1.3 |  |  | Design in Crystal Report | 21/10/2019 | 25/10/2019 | 5 | Completed
1.4 |  | Page 3 (หัวข้อการตรวจสอบความปลอดภัยของเครื่องจักรและอุปกรณ์ - Change New Report)
1.5 |  |  | Design in asp.net HTML Bootstrap | 02/06/2020 | 10/06/2020 | 9 | Completed
1.6 |  |  | Design in Crystal Report | 11/06/2020 | 22/06/2020 | 12 | Completed
2 | Build & Development
2.1 |  | Page 2 (Equipment Safety Device & Safety Cover Check Sheet)
2.2 |  |  | Perform system development coding in visual studio | 04/11/2019 | 16/11/2019 | 13 | Completed
2.3 |  |  | Function Test in visual studio | 17/11/2019 | 19/11/2019 | 3 | Completed
2.4 |  |  | Perform system development coding in crystal report | 20/11/2019 | 29/11/2019 | 10 | Completed
2.5 |  |  | Function Test in cryatal report | 30/11/2019 | 04/12/2020 | 4 | Completed
2.6 |  | Page 3 (หัวข้อการตรวจสอบความปลอดภัยของเครื่องจักรและอุปกรณ์ - Change New Report)
2.7 |  |  | Perform system development coding in visual studio | 23/06/2020 | 10/07/2020 | 16 | Completed
2.8 |  |  | Function Test in visual studio | 11/07/2020 | 14/07/2020 | 4 | Completed
2.9 |  |  | Perform system development coding in crystal report | 15/07/2020 | 26/07/2020 | 12 | Delay
2.10 |  |  | Function Test in cryatal report | 27/07/2020 | 28/07/2020 | 2 | Delay
3 | Deployment
3.1 |  | Prepare testing environment |  | 08/10/2020 | 09/10/2020 | 2 | Delay | [5 empty] | o | o
3.2 |  | UAT test |  | 12/10/2020 | 13/10/2020 | 2 | Delay | [7 empty] | o | o
3.3 |  | System launch |  | 14/10/2020 | 15/10/2020 | 2 | Delay | [9 empty] | o | o
3.4 |  | Sign Off Project |  | 16/10/2020 | 16/10/2020 | 1 | Delay | [11 empty] | o

## Sheet2
Page 3:Report(Change report page 3 New standard from ROHM)
Old Report page 3 | New Report page 3/1 | New Report page 3/2