## Sheet1
RIST MACHINE REGISTER PLAN
[8 empty] | June #6 | [27 empty] | July #7 | [27 empty] | August #8
Task ID | Task |  |  | Start Date | End Date | Duration (Days) | Status | 2020-06-01 | [6 empty] | 2020-06-08 | [6 empty] | 2020-06-15 | [6 empty] | 2020-06-22 | [6 empty] | 2020-07-01 | [6 empty] | 2020-07-08 | [6 empty] | 2020-07-15 | [6 empty] | 2020-07-22 | [6 empty] | 2020-08-01 |  |  |  |  | 2020-08-08 |  |  |  |  | 2020-08-15 | 2020-08-22
1 | Design interface and report
1.1 |  | Page 2 (Equipment Safety Device & Safety Cover Check Sheet)
1.2 |  |  | Design in asp.net HTML Bootstrap | 18/10/2019 | 19/10/2019 | 3 | Completed
1.3 |  |  | Design in Crystal Report | 21/10/2019 | 25/10/2019 | 5 | Completed
1.4 |  | Page 3 (หัวข้อการตรวจสอบความปลอดภัยของเครื่องจักรและอุปกรณ์ - Change New Report)
1.5 |  |  | Design in asp.net HTML Bootstrap | 2020-02-06 | 2020-10-06 | 9 |  |  | o | o | o | o | o | o | o | o | o
1.6 |  |  | Design in Crystal Report | 2020-11-06 | 22/06/2020 | 12 | [11 empty] | o | o | o | o | o | o | o | o | o | o | o | o
2 | Build & Development
2.1 |  | Page 2 (Equipment Safety Device & Safety Cover Check Sheet)
2.2 |  |  | Perform system development coding in visual studio | 2019-04-11 | 16/11/2019 | 13 | Completed
2.3 |  |  | Function Test in visual studio | 17/11/2019 | 19/11/2019 | 3 | Completed
2.4 |  |  | Perform system development coding in crystal report | 20/11/2019 | 29/11/2019 | 10 | Completed
2.5 |  |  | Function Test in cryatal report | 30/11/2019 | 2019-04-12 | 4 | Completed
2.6 |  | Page 3 (หัวข้อการตรวจสอบความปลอดภัยของเครื่องจักรและอุปกรณ์ - Change New Report)
2.7 |  |  | Perform system development coding in visual studio | 23/06/2020 | 2020-10-07 | 16 | Delay | [22 empty] | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o
2.8 |  |  | Function Test in visual studio | 2020-11-07 | 14/07/2020 | 4 | Delay | [38 empty] | o | o | o | o
2.9 |  |  | Perform system development coding in crystal report | 15/07/2020 | 26/07/2020 | 12 | Delay | [42 empty] | o | o | o | o | o | o | o | o | o | o | o | o
2.10 |  |  | Function Test in cryatal report | 27/07/2020 | 2020-07-08 | 2 | Delay | [54 empty] | o | o
3 | Deployment
3.1 |  | Prepare testing environment |  | 2020-04-08 | 2020-05-08 | 2 | Delay | [57 empty] | o | o
3.2 |  | UAT test |  | 2020-06-08 | 2020-07-08 | 2 | Delay | [59 empty] | o | o
3.3 |  | System launch |  | 2020-10-08 | 2020-12-08 | 2 | Delay | [62 empty] | o | o | o
3.4 |  | Sign Off Project |  | 13/08/2020 | 13/08/2020 | 1 | Delay | [65 empty] | o

## Sheet2
Page 3:Report(Change report page 3 New standard from ROHM)
Old Report page 3 | New Report page 3/1 | New Report page 3/2